## Gantt Chart
CHATBOT DEVELOPMENT PLAN
PROJECT TITLE |  | ChatBot for web |  |  |  |  | COMPANY NAME | [6 empty] | ABC
PROJECT MANAGER |  | Elvis Wong |  |  |  |  | DATE | [6 empty] | 2020-11-01
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Requirments Gathering
1.1 | information gathering |  | 2020-11-01 | 2020-11-06 | 5 | 100% | bar: WEEK 1 M to WEEK 2 M
1.1.1 | - meeting section with Sales |  | 2020-11-01 | 2020-11-03 | 2 | 100% | bar: WEEK 1 M to WEEK 1 T; WEEK 2 M
1.1.2 | - meeting section with Marketing |  | 2020-11-02 | 2020-11-04 | 2 | 90% | bar: WEEK 1 T to WEEK 1 W; WEEK 2 M
1.1.3 | - meeting section with Services |  | 2020-11-03 | 2020-11-05 | 2 | 90% | bar: WEEK 1 W to WEEK 1 R; WEEK 2 M
1.1.4 | - meeting section with MIS |  | 2020-11-04 | 2020-11-06 | 2 | 70% | bar: WEEK 1 R to WEEK 2 M
1.2 | information Sharing / confirmation |  | 2020-11-07 | 2020-11-07 | 1 | 60% | bar: WEEK 2 M
2 | Scope Analysis
2.1 | Scope and Goal Setting |  | 2020-11-07 | 2020-11-07 | 1 | 22% | bar: WEEK 2 M
2.2 | Budgeting |  | 2020-11-07 | 2020-11-07 | 1 | 16% | bar: WEEK 2 M
2.3 | Communication Plan |  | 2020-11-08 | 2020-11-08 | 1 | 0% | bar: WEEK 2 M to WEEK 2 T
2.4 | Risk Management |  | 2020-11-09 | 2020-11-09 | 1 | 0% | bar: WEEK 2 M; WEEK 2 W
2.5 | KPIs setting |  | 2020-11-10 | 2020-11-10 | 1 | 0% | bar: WEEK 2 M; WEEK 2 R
3 | Solution Design
3.1 | Functional request |  | 2020-11-11 | 2020-11-11 | 1 | 0% | bar: WEEK 2 M; WEEK 2 F
3.2 | Non-function request |  | 2020-11-12 | 2020-11-12 | 1 | 0% | bar: WEEK 2 M; WEEK 3 M
3.3 | Software Architecture |  | 2020-11-13 | 2020-11-14 | 2 | 0% | bar: WEEK 2 M; WEEK 3 T to WEEK 3 W
3.4 | Hardware Architecture |  | 2020-11-16 | 2020-11-17 | 2 | 0% | bar: WEEK 2 M; WEEK 3 R to WEEK 3 F
4 | Development
4.1 | Coding |  | 2020-11-20 | 2020-12-07 | 18 | 0% | bar: WEEK 2 M; WEEK 4 W to WEEK 7 F
4.2 | Setup & Installation |  | 2020-12-02 | 2020-12-12 | 11 | 0% | bar: WEEK 2 M; WEEK 6 F to WEEK 8 F
4.3 | Testing & Debug |  | 2020-12-11 | 2020-12-14 | 4 | 0% | bar: WEEK 2 M; WEEK 8 R to WEEK 9 T
4.4 | Effort and Cost Tracking |  | 2020-12-15 | 2020-12-16 | 2 | 0% | bar: WEEK 2 M; WEEK 9 W to WEEK 9 R
5 | User Acceptance Test
5.1 | User Testing |  | 2020-12-16 | 2020-12-21 | 6 | 0% | bar: WEEK 2 M; WEEK 9 R to WEEK 10 R
5.2 | Correction / Enhancement |  | 2020-12-22 | 2020-12-26 | 5 | 0% | bar: WEEK 2 M; WEEK 10 F to WEEK 11 R
6 | Admin
6.1 | Setup & Installation |  | 2020-12-21 | 2020-12-29 | 9 | 0% | bar: WEEK 2 M; WEEK 10 R to WEEK 12 T
6.2 | Effort and Cost Tracking |  | 2020-12-30 | 2020-12-31 | 2 | 0% | bar: WEEK 2 M; WEEK 12 W to WEEK 12 R
6.3 | Project Review meeting |  | 2020-12-31 | 2021-01-01 | 2 | 0% | bar: WEEK 2 M; WEEK 2 F; WEEK 4 T; WEEK 6 F; WEEK 9 R; WEEK 10 R to WEEK 10 F; WEEK 11 F; WEEK 12 R to WEEK 12 F